## Dashboard
PROJECT REPORT - Mission Control
Today |  | Tomorrow |  | Week Of (Mon)
READY NOW |  |  |  | TOP BLOCKERS
Task | Owner | Action | Blocked By | Blocked Task | Owner | Blocker(s) | Call Now?

## LookAhead (Field)
LookAhead (Field) — Prev / This / Next / Forward-Private
Boss prints Prev/This/Next. Forward-Private is for you only.
Phase | Company | Task | Notes | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat
Legend |  |  |  | X=Performed | /=Scheduled | 0=Behind | !=Inspection

## Gantt (Print)
Gantt (Print)
Generated by Office Script logic.

## Task_Status
Task Status
Field truth sheet for status, inspections, and contacts.
Task_ID | Task_Name | OwnerCompany | Status | Confirmed_Complete | Inspection_Required | Inspection_Passed | Last_Updated | Call_Now | Phase | Trade | Contact_Name | Phone | Email

## Graph Engine
Graph Engine
Generated dependency network for schedule logic.
Nodes
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade

## Graph Unlock
Graph Unlock
Ready-now and blocker logic for dispatch.
Task_ID | Task_Name | OwnerCompany | Ready_Now | Blocked_By | Call_Now | Requires_Inspection | Phase | Trade

## Critical Path
Critical Path
Critical-path output generated by Apps Script.
Task_ID | Task_Name | Duration_Days | Earliest_Start | Earliest_Finish | Latest_Start | Latest_Finish | Slack_Days | Is_Critical

## Sequence
Sequence (Field Scope)
Base sequence rows for the current project.
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade

## Project Info
Key | Value

## Company Profiles
Trade Company Map
Store the best field contact for each trade here. The app uses the primary contact first.
Company | Trade | Contact_Name | Phone | Email | Contact_Role | Primary

## Settings
Key | Value
ThisWeekStart
PreparedBy | Superintendent
ShowBossWeeks | 3
BossHideForwardWeek | TRUE
DefaultSequencePack | House_NewConstruction
DefaultRunMode | TwoWeek
AutomationHour | 5
BossEmailTo
BossEmailCc
AttachPdfOnBossEmail | TRUE
TemplateVersion | v1.0

## Email_Boss
Output generated by Office Script

## 2-week
2-week
Project Name: | [14 empty] | Prepared By:
Job Description | Past Week of: | [5 empty] | This Week of: | [5 empty] | Next Week of: | [5 empty] | SubContractor
| M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S
Phase | Past Week of: M: Task ID; Past Week of: T: Task Name; Past Week of: W: OwnerCompany; Past Week of: T: Status; Past Week of: F: Ready_Now; Past Week of: S: Blocked_By; This Week of: M: Call_Now

## Daily_Log
Daily Field Log
One row per field report from the app.
Entry_Timestamp | Report_Date | Prepared_By | Weather | Site_Headcount | On_Site_Companies | Scheduled_Tomorrow | Inspections_Needed | Inspections_Passed_Today | Deliveries | Blockers | Decisions_Needed | Notes

## Cost_Log
Cost Log
Estimates, purchase orders, invoices, and payments.
Entry_Timestamp | Cost_Date | Type | Vendor | Category | Amount | Due_Date | Status | Notes

## Sequence_Additions
Sequence Additions
Ad hoc tasks layered on top of the selected pack.
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade

## Sequence_Condo_BathRemodel
Sequence Condo BathRemodel
Source sequence pack used by the Google Sheets app.
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade
CB-001 | Scope confirmation and unit access plan | 1 |  | Prime Builders | N | N | Preconstruction | Planning
CB-002 | Material lead check and sub lock | 1 | CB-001 | Prime Builders | N | N | Preconstruction | Planning
CB-003 | Protection setup and dust control | 1 | CB-002 | Prime Builders | N | N | Demolition | General Conditions
CB-004 | Selective bath demolition | 2 | CB-003 | Prime Builders | N | N | Demolition | Demo
CB-005 | Hub and Tack layout for fixture centers | 1 | CB-004 | Prime Builders | N | Y | Rough-In | Layout
CB-006 | Plumbing rough-in adjustments | 2 | CB-005 | FlowCore Plumbing | Y | Y | Rough-In | Plumbing
CB-007 | Electrical rough-in updates | 2 | CB-005 | Sparkline Electric | Y | Y | Rough-In | Electrical
CB-008 | Rough framing corrections and backing | 1 | CB-005 | FrameRight Carpentry | N | N | Rough-In | Carpentry
CB-009 | Rough inspection closeout | 1 | CB-006,CB-007 | Prime Builders | Y | Y | Inspection | Inspection
CB-010 | Waterproofing and shower pan test | 2 | CB-009 | TileForm Studio | Y | Y | Close-In | Tile Prep
CB-011 | Tile install and grout | 3 | CB-010 | TileForm Studio | N | N | Finishes | Tile
CB-012 | Vanity and cabinet install | 1 | CB-011 | Urban Grain Millwork | N | N | Finishes | Millwork
CB-013 | Fixture trim and MEP final tie-in | 2 | CB-012 | Prime Builders | Y | Y | Finish MEP | MEP Final
CB-014 | Punchlist and final clean | 1 | CB-013 | Prime Builders | N | Y | Closeout | Closeout

## Sequence_Condo_FullRemodel
Sequence Condo FullRemodel
Source sequence pack used by the Google Sheets app.
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade
CF-001 | Design freeze and permit package | 4 |  | Prime Builders | Y | N | Preconstruction | Planning
CF-002 | Submittal approvals and procurement | 3 | CF-001 | Prime Builders | N | N | Preconstruction | Planning
CF-003 | Site logistics and full protection | 1 | CF-002 | Prime Builders | N | N | Demolition | General Conditions
CF-004 | Full interior demolition | 4 | CF-003 | Prime Builders | N | N | Demolition | Demo
CF-005 | Hub and Tack whole-unit control points | 1 | CF-004 | Prime Builders | N | Y | Rough-In | Layout
CF-006 | Structural carpentry corrections | 3 | CF-005 | FrameRight Carpentry | Y | Y | Structure | Carpentry
CF-007 | Electrical rough-in complete | 4 | CF-006 | Sparkline Electric | Y | Y | Rough-In | Electrical
CF-008 | Plumbing rough-in complete | 4 | CF-006 | FlowCore Plumbing | Y | Y | Rough-In | Plumbing
CF-009 | HVAC rough-in complete | 3 | CF-006 | BluePeak Mechanical | Y | Y | Rough-In | HVAC
CF-010 | Rough plumbing inspection | 1 | CF-008 | Prime Builders | Y | Y | Inspection | Plumbing Inspection
CF-011 | Rough electrical inspection | 1 | CF-007 | Prime Builders | Y | Y | Inspection | Electrical Inspection
CF-012 | Rough HVAC inspection | 1 | CF-009 | Prime Builders | Y | Y | Inspection | HVAC Inspection
CF-013 | Insulation install | 2 | CF-010,CF-011,CF-012 | Northwall Interiors | N | N | Close-In | Insulation
CF-014 | Drywall hang | 3 | CF-013 | Northwall Interiors | N | N | Close-In | Drywall
CF-015 | Drywall finish and texture | 3 | CF-014 | Northwall Interiors | N | N | Close-In | Drywall
CF-016 | Prime walls | 1 | CF-015 | FinishCraft LLC | N | N | Close-In | Paint
CF-017 | Cabinetry and trim install | 4 | CF-016 | Urban Grain Millwork | N | N | Finishes | Millwork
CF-018 | Countertops and tile finish | 3 | CF-017 | StoneLine Surfaces | N | N | Finishes | Countertops/Tile
CF-019 | Paint and final fixture trim | 3 | CF-018 | FinishCraft LLC | N | N | Finishes | Paint/Fixtures
CF-020 | Final MEP inspections and turnover | 2 | CF-019 | Prime Builders | Y | Y | Closeout | Closeout

## Sequence_Condo_PartialRemodel
Sequence Condo PartialRemodel
Source sequence pack used by the Google Sheets app.
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade
CP-001 | Field verify partial scope | 1 |  | Prime Builders | N | N | Preconstruction | Planning
CP-002 | Procurement and delivery lock | 1 | CP-001 | Prime Builders | N | N | Preconstruction | Planning
CP-003 | Protection and controlled demolition | 2 | CP-002 | Prime Builders | N | N | Demolition | Demo
CP-004 | Hub and Tack control lines | 1 | CP-003 | Prime Builders | N | Y | Rough-In | Layout
CP-005 | Electrical rough updates | 2 | CP-004 | Sparkline Electric | Y | Y | Rough-In | Electrical
CP-006 | Plumbing rough updates | 2 | CP-004 | FlowCore Plumbing | Y | Y | Rough-In | Plumbing
CP-007 | HVAC branch adjustment | 1 | CP-004 | BluePeak Mechanical | Y | Y | Rough-In | HVAC
CP-008 | Rough plumbing inspection | 1 | CP-006 | Prime Builders | Y | Y | Inspection | Plumbing Inspection
CP-009 | Rough electrical inspection | 1 | CP-005 | Prime Builders | Y | Y | Inspection | Electrical Inspection
CP-010 | Rough HVAC inspection | 1 | CP-007 | Prime Builders | Y | Y | Inspection | HVAC Inspection
CP-011 | Drywall patch and finish prep | 2 | CP-008,CP-009,CP-010 | Northwall Interiors | N | N | Close-In | Drywall
CP-012 | Prime and paint | 2 | CP-011 | FinishCraft LLC | N | N | Finishes | Paint
CP-013 | Casework and trim touchups | 2 | CP-012 | Urban Grain Millwork | N | N | Finishes | Millwork
CP-014 | Fixture reset and system checks | 2 | CP-013 | Prime Builders | N | Y | Closeout | Closeout

## Sequence_House_BathRemodel
Sequence House BathRemodel
Source sequence pack used by the Google Sheets app.
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade
HB-001 | Homeowner scope lock and permit check | 2 |  | Prime Builders | Y | N | Preconstruction | Planning
HB-002 | Staging and isolation setup | 1 | HB-001 | Prime Builders | N | N | Demolition | General Conditions
HB-003 | Bath selective demolition | 2 | HB-002 | Prime Builders | N | N | Demolition | Demo
HB-004 | Hub and Tack layout for walls and fixtures | 1 | HB-003 | Prime Builders | N | Y | Rough-In | Layout
HB-005 | Carpentry backing and framing correction | 2 | HB-004 | FrameRight Carpentry | N | N | Rough-In | Carpentry
HB-006 | Plumbing rough relocation | 2 | HB-004 | FlowCore Plumbing | Y | Y | Rough-In | Plumbing
HB-007 | Electrical rough relocation | 2 | HB-004 | Sparkline Electric | Y | Y | Rough-In | Electrical
HB-008 | Rough inspection closeout | 1 | HB-006,HB-007 | Prime Builders | Y | Y | Inspection | Inspection
HB-009 | Shower prep waterproofing and pan test | 2 | HB-008 | TileForm Studio | Y | Y | Close-In | Tile Prep
HB-010 | Tile and grout completion | 3 | HB-009 | TileForm Studio | N | N | Finishes | Tile
HB-011 | Vanity tops and trim | 2 | HB-010 | Urban Grain Millwork | N | N | Finishes | Millwork
HB-012 | Final fixture trim and owner walk | 2 | HB-011 | Prime Builders | Y | Y | Closeout | Closeout

## Sequence_House_FullRemodel
Sequence House FullRemodel
Source sequence pack used by the Google Sheets app.
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade
HF-001 | Design freeze structural review and permit set | 5 |  | Prime Builders | Y | N | Preconstruction | Planning
HF-002 | Long-lead procurement and schedule lock | 4 | HF-001 | Prime Builders | N | N | Preconstruction | Planning
HF-003 | Site logistics temporary utilities and protection | 2 | HF-002 | Prime Builders | N | N | Demolition | General Conditions
HF-004 | Full demolition and debris removal | 5 | HF-003 | Prime Builders | N | N | Demolition | Demo
HF-005 | Hub and Tack whole-house baseline layout | 1 | HF-004 | Prime Builders | N | Y | Rough-In | Layout
HF-006 | Structural framing and shear corrections | 4 | HF-005 | FrameRight Carpentry | Y | Y | Structure | Carpentry
HF-007 | Electrical rough whole-house | 5 | HF-006 | Sparkline Electric | Y | Y | Rough-In | Electrical
HF-008 | Plumbing rough whole-house | 5 | HF-006 | FlowCore Plumbing | Y | Y | Rough-In | Plumbing
HF-009 | HVAC rough whole-house | 4 | HF-006 | BluePeak Mechanical | Y | Y | Rough-In | HVAC
HF-010 | Rough plumbing inspection | 1 | HF-008 | Prime Builders | Y | Y | Inspection | Plumbing Inspection
HF-011 | Rough electrical inspection | 1 | HF-007 | Prime Builders | Y | Y | Inspection | Electrical Inspection
HF-012 | Rough HVAC inspection | 1 | HF-009 | Prime Builders | Y | Y | Inspection | HVAC Inspection
HF-013 | Insulation install | 2 | HF-010,HF-011,HF-012 | Northwall Interiors | N | N | Close-In | Insulation
HF-014 | Drywall hang | 3 | HF-013 | Northwall Interiors | N | N | Close-In | Drywall
HF-015 | Drywall finish | 4 | HF-014 | Northwall Interiors | N | N | Close-In | Drywall
HF-016 | Prime walls | 2 | HF-015 | FinishCraft LLC | N | N | Close-In | Paint
HF-017 | Cabinet install countertops and trim | 5 | HF-016 | Urban Grain Millwork | N | N | Finishes | Millwork
HF-018 | Paint floor finish and punch prep | 4 | HF-017 | FinishCraft LLC | N | N | Finishes | Paint/Flooring
HF-019 | Final MEP trim and finals inspection | 3 | HF-018 | Prime Builders | Y | Y | Closeout | Closeout
HF-020 | Client walkthrough and turnover | 1 | HF-019 | Prime Builders | N | Y | Closeout | Handover

## Sequence_House_NewConstruction
Sequence House NewConstruction
Source sequence pack used by the Google Sheets app.
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade
HN-001 | Permit release and notice to proceed | 3 |  | Prime Builders | Y | N | Preconstruction | Permitting
HN-002 | Site mobilization and safety controls | 2 | HN-001 | Prime Builders | N | N | Sitework | General Conditions
HN-003 | Temp irrigation erosion controls and site utilities | 2 | HN-002 | Prime Builders | N | Y | Sitework | Site Utilities
HN-004 | Layout staking hub and tack control network | 2 | HN-003 | Prime Builders | N | Y | Sitework | Layout
HN-005 | Excavation and footings | 4 | HN-004 | Prime Builders | Y | Y | Foundation | Concrete
HN-006 | Underground plumbing and sleeves | 3 | HN-005 | FlowCore Plumbing | Y | Y | Foundation | Plumbing
HN-007 | HVAC underground sleeves and chases | 2 | HN-005 | BluePeak Mechanical | Y | Y | Foundation | HVAC
HN-008 | Stem walls slab prep and pour | 5 | HN-005,HN-006,HN-007 | Prime Builders | Y | Y | Foundation | Concrete
HN-009 | Truss delivery and staging | 1 | HN-008 | FrameRight Carpentry | N | Y | Structure | Material Delivery
HN-010 | Wall framing | 5 | HN-008 | FrameRight Carpentry | Y | Y | Structure | Framing
HN-011 | Truss set | 2 | HN-009,HN-010 | FrameRight Carpentry | Y | Y | Structure | Framing
HN-012 | Roof sheathing | 2 | HN-011 | FrameRight Carpentry | N | N | Structure | Framing
HN-013 | Dry-in icing and underlayment | 2 | HN-012 | FrameRight Carpentry | Y | Y | Envelope | Roofing
HN-014 | Sheathing and dry-in inspection | 1 | HN-013 | Prime Builders | Y | Y | Inspection | Envelope Inspection
HN-015 | Buck install | 2 | HN-014 | FrameRight Carpentry | N | Y | Envelope | Openings
HN-016 | Buck waterproofing | 1 | HN-015 | FrameRight Carpentry | N | N | Envelope | Waterproofing
HN-017 | Buck inspection | 1 | HN-016 | Prime Builders | Y | Y | Inspection | Openings Inspection
HN-018 | Window delivery | 1 | HN-013 | Prime Builders | N | Y | Envelope | Material Delivery
HN-019 | Window install | 3 | HN-017,HN-018 | FrameRight Carpentry | N | Y | Envelope | Openings
HN-020 | Water test | 1 | HN-019 | Prime Builders | Y | Y | Inspection | Envelope Testing
HN-021 | Window inspection | 1 | HN-020 | Prime Builders | Y | Y | Inspection | Openings Inspection
HN-022 | Lightning protection rough | 2 | HN-014 | BluePeak Mechanical | N | Y | Envelope | Lightning Protection
HN-023 | Soffit install | 2 | HN-013 | FrameRight Carpentry | N | N | Envelope | Finish Carpentry
HN-024 | Fascia install | 2 | HN-013 | FrameRight Carpentry | N | N | Envelope | Finish Carpentry
HN-025 | Rough plumbing top-out | 5 | HN-014 | FlowCore Plumbing | Y | Y | Rough-In | Plumbing
HN-026 | Rough electrical top-out | 5 | HN-014 | Sparkline Electric | Y | Y | Rough-In | Electrical
HN-027 | Rough HVAC top-out | 4 | HN-014 | BluePeak Mechanical | Y | Y | Rough-In | HVAC
HN-028 | Rough plumbing inspection | 1 | HN-025 | Prime Builders | Y | Y | Inspection | Plumbing Inspection
HN-029 | Rough electrical inspection | 1 | HN-026 | Prime Builders | Y | Y | Inspection | Electrical Inspection
HN-030 | Rough HVAC inspection | 1 | HN-027 | Prime Builders | Y | Y | Inspection | HVAC Inspection
HN-031 | Spray insulation | 2 | HN-021,HN-022,HN-028,HN-029,HN-030 | Northwall Interiors | N | Y | Close-In | Insulation
HN-032 | Drywall hang | 3 | HN-031 | Northwall Interiors | N | N | Close-In | Drywall
HN-033 | Drywall finish | 4 | HN-032 | Northwall Interiors | N | N | Close-In | Drywall
HN-034 | Prime walls | 2 | HN-033 | FinishCraft LLC | N | N | Close-In | Paint
HN-035 | Interior millwork cabinets and trim | 6 | HN-034 | Urban Grain Millwork | N | N | Finishes | Millwork
HN-036 | Flooring paint and tile finishes | 6 | HN-035 | FinishCraft LLC | N | N | Finishes | Interior Finishes
HN-037 | Landscape irrigation and exterior utility trim | 3 | HN-024,HN-019 | Prime Builders | N | Y | Sitework | Landscape Irrigation
HN-038 | Propane tank set and utility startup | 2 | HN-037 | Prime Builders | Y | Y | Sitework | Gas Utility
HN-039 | Final MEP trim and startup | 4 | HN-036 | Prime Builders | Y | Y | Commissioning | MEP Final
HN-040 | Final inspections punch and CO handoff | 3 | HN-038,HN-039 | Prime Builders | Y | Y | Closeout | Closeout

## Sequence_House_PartialRemodel
Sequence House PartialRemodel
Source sequence pack used by the Google Sheets app.
Task_ID | Task_Name | Duration_Days | Predecessors | OwnerCompany | Requires_Inspection | Call_Now | Phase | Trade
HP-001 | Partial remodel scope and sequencing plan | 2 |  | Prime Builders | N | N | Preconstruction | Planning
HP-002 | Procurement and long-lead release | 2 | HP-001 | Prime Builders | N | N | Preconstruction | Planning
HP-003 | Selective demolition by zone | 3 | HP-002 | Prime Builders | N | N | Demolition | Demo
HP-004 | Hub and Tack zone control lines | 1 | HP-003 | Prime Builders | N | Y | Rough-In | Layout
HP-005 | Electrical rough updates | 3 | HP-004 | Sparkline Electric | Y | Y | Rough-In | Electrical
HP-006 | Plumbing rough updates | 3 | HP-004 | FlowCore Plumbing | Y | Y | Rough-In | Plumbing
HP-007 | HVAC branch rework | 2 | HP-004 | BluePeak Mechanical | Y | Y | Rough-In | HVAC
HP-008 | Rough plumbing inspection | 1 | HP-006 | Prime Builders | Y | Y | Inspection | Plumbing Inspection
HP-009 | Rough electrical inspection | 1 | HP-005 | Prime Builders | Y | Y | Inspection | Electrical Inspection
HP-010 | Rough HVAC inspection | 1 | HP-007 | Prime Builders | Y | Y | Inspection | HVAC Inspection
HP-011 | Drywall patch and hang | 2 | HP-008,HP-009,HP-010 | Northwall Interiors | N | N | Close-In | Drywall
HP-012 | Drywall finish and texture blend | 2 | HP-011 | Northwall Interiors | N | N | Close-In | Drywall
HP-013 | Prime walls | 1 | HP-012 | FinishCraft LLC | N | N | Close-In | Paint
HP-014 | Paint and finish carpentry touchups | 3 | HP-013 | FinishCraft LLC | N | N | Finishes | Paint/Trim
HP-015 | Final fixture reset and QA pass | 2 | HP-014 | Prime Builders | N | Y | Closeout | Closeout